## Sheet1
Tasks | 2014-02-01 | 2014-02-08 | 2014-02-15 | 2014-02-22 | 2014-03-01 | 2014-03-08 | 2014-03-15 | 2014-03-22 | 2014-03-29 | 2014-04-05 | 2014-04-12 | 2014-04-19 | 2014-04-26 | 2014-05-03 | 2014-05-10 | 2014-05-17 | 2014-05-24 | 2014-05-31 | 2014-06-07 | 2014-06-14 | 2014-06-21 | 2014-06-28 | 2014-07-05 | 2014-07-12
Basic Plan
Rationale | bar: 2014-02-01
Timeline | bar: 2014-02-01
Basic Game Design | bar: 2014-02-01
Ground Work
Interview with target audience | bar: 2014-02-22
(Possible) Interview with people acquainted with game design | bar: 2014-03-01
Basic movement
Advanced Movement | bar: 2014-02-01
Collision detection | bar: 2014-02-15
Core mechanics
Mapping mouse to rotation | bar: 2014-02-22
Sound algorithim written | bar: 2014-02-01
Test sounds encoded | bar: 2014-03-15
Projectiles | bar: 2014-03-22
Not moving targets | bar: 2014-03-29
Health + hit detection | bar: 2014-04-05
Polishing
Proper sounds implemented | bar: 2014-04-19
Multiplayer server support | bar: 2014-05-24
Menu + respawning + death sounds | bar: 2014-06-21
Removal of debugging graphics | bar: 2014-06-28
Key
D | 2014-02-01: Done
X | 2014-02-01: Deadline
pg.8