## Sheet1
Tasks: Includes research as well as completing said tasks | 2014-02-01 | 2014-02-08 | 2014-02-15 | 2014-02-22 | 2014-03-01 | 2014-03-08 | 2014-03-15 | 2014-03-22 | 2014-03-29 | 2014-04-05 | 2014-04-12 | 2014-04-19 | 2014-04-26 | 2014-05-03 | 2014-05-10 | 2014-05-17 | 2014-05-24 | 2014-05-31 | 2014-06-07 | 2014-06-14 | 2014-06-21 | 2014-06-28 | 2014-07-05 | 2014-07-12 | 2014-07-19 | 2014-07-26 | 2014-08-02 | 2014-08-09 | 2014-08-16 | 2014-08-23 | 2014-08-30 | 2014-09-06 | 2014-09-13 | 2014-09-20 | 2014-09-27
Basic Plan
Rationale | bar: 2014-02-01
Timeline | bar: 2014-02-01
Basic Game Design | bar: 2014-02-01
Ground Work
Interview with target audience | bar: 2014-04-12
(Possible) Interview with people acquainted with game design
Basic movement | bar: 2014-02-01
Advanced Movement | bar: 2014-02-01
Collision detection with walls | bar: 2014-02-22
Core mechanics
Mapping mouse to rotation
Sound algorithim written | bar: 2014-02-01
Sounds made | bar: 2014-08-16
Test sound encoded | bar: 2014-06-21
Projectiles | bar: 2014-06-21
Not moving targets | bar: 2014-06-21
Moving targets | bar: 2014-06-21
Health + hit detection | bar: 2014-07-12
Addition of weapon types | bar: 2014-08-02
Addition of multiple maps | bar: 2014-08-09
Polishing
Proper sounds implemented | bar: 2014-08-23
Multiplayer server support
Menu + respawning + death sounds | bar: 2014-08-30
Removal of debugging graphics | bar: 2014-09-06
Key
D | 2014-02-01: Done
X | 2014-02-01: Deadline